## Deployment Planning
FULL BOOK DEPLOYMENT PLAN | 8/24-8/27 | 8/31-9/4 |  |  | 9/7-9/11 | 9/14-9/18 | 9/21-9/25 | 9/28-10/1 | 10/5-10-9 | 10/12-10/16 | 10/19-10/23 | 10/26-10/30 | 11/2-11/6 | 11/9-11/13 | 11/16-11/20 | 11/23- 11-27 | 11/30-12/4 | 12/7-12/11 | 12/14-12/19 | 12/21-12/25 | 12/28-1/1 | 1/4-1/8 | 1/11-1/15 | 1/18-1/22 | 1/25-1/29 | 2/1-2/5 | 2/8-2/12 | 2/15-2/19 | 2/22-2/26 | 3/1-3/5 | 3/8-3/12 | 3/15-3/19 | 3/22-3/26 | 3/29-4/2 | 4/5-4/9 | 4/12-4/16 | 4/19-4/23 | 4/26-4/30 | 5/3-5/7 | 5-10-5/14 | 5/17-5/21 | 5/24-5/28 | 5/31-6/4 | 6/7-6/11 | 6/14-6/18 | 6/21-6/25 | 6/28-7/2
DEPLOYMENT 2
Diabetes | [8 empty] | TESTING Starts | [9 empty] | Deploy
Full Book
Cadence | [8 empty] | TESTING Starts | [9 empty] | Deploy
SFMC for CKD | [14 empty] | TESTING STARTS |  |  | UAT | Deploy
DEPLOYMENT 1 | [12 empty] | Diabetes | [5 empty] | Diabetes deploy
New scope |  |  | rationalization #1 & #2 Priority | Dev Hours | Total Dev Weeks | Weeks with multiple developers | # developers
Privacy API (EPIC B/E, UI, ESL, IPP) |  |  | Need level of effort and coordination with other teams to commit to deployment date- Year end Freeze | TBD |  |  |  |  | Requirements |  | DESIGN | DESIGN | BUILD (WORKFLOWS/UI/INTEGRATIONS-EPIC/IPP) Regression EPH Only | [6 empty] | QA |  |  | UAT |  | train | Deploy
ingest ADT (possibly tied to Care everywhere) |  |  |  | TBD | [6 empty] | Requirements |  |  | Design |  | Development |  |  |  |  | QA |  | UAT |  | train | Deploy
DEPLOYMENT 2
Full Book |  |  | To support a March month-end release requirements need to be approved by 10/30 | Dev Hours | Total Dev Weeks | Weeks with multiple developers | # developers | [20 empty] | QA can only start here -post Warranty
MEP integration (#8 & #10) |  |  | Rationalization MEP & MyChar & Cadence dependencies | 310 | 7.75 | 3.875 | 2(dev) |  | Requirements |  |  |  | Design | Design | Dev (assuming 4 weeks 2 developers) |  |  |  | QA |  |  |  | E2E |  |  | UAT |  |  | Train |  |  |  | Deploy | Deploy
My Chart w/(#9) |  |  |  | 1740 | 43.5 | 10.875 | (4 Dev) |  | Requirements |  |  |  | Design | Design | Dev |  | Dev (Assume11 weeks 4 developers) | [7 empty] | QA |  |  | E2E | /E2E UAT/Train
Cadence Group Coaching |  |  | Waiting on Tracey(intergration Requirements TBD) | [5 empty] | Requirements |  |  |  | Design | Design
DEPLOYMENT 3
|  |  | Rationalization | Dev Hours | Total Dev Weeks | Weeks with multiple developers | # developers
Full SFMC Functionality (#7& #20b) |  |  |  | 1240 | 31 | 10.3333 | (3 Dev) |  |  |  | Requirements |  |  |  | Design | Design |  | Dev (Assume 10 weeks 3 developers) | [8 empty] | QA | [5 empty] | Deploy
Auto Status |  |  | Need more information | [9 empty] | Requirements | [6 empty] | DEV | [6 empty] | QA | [5 empty] | E2E |  |  | UAT/Train |  |  | Deploy
Care Everywhere (kidney and Diabetes |  |  | Team deploys independently (could move up) | 300 | 7.5 | [7 empty] | Requirements | [6 empty] | DEV | [6 empty] | QA | [5 empty] | E2E |  |  | UAT/Train |  |  | Deploy
Healthy Planet?? |  |  | Need more information | TBD | [8 empty] | Requirements | [6 empty] | DEV | [6 empty] | QA | [5 empty] | E2E |  |  | UAT/Train |  |  | Deploy
DEPLOYMENT 4 | [26 empty] | QA | [5 empty] | E2E |  |  | UAT/Train
|  |  | Rationalization | Dev Hours | Total Dev Weeks | Weeks with multiple developers | # developers
Lexis/Compact Nurse |  |  | Alignment with vendor | [9 empty] | Requirements | [12 empty] | Lexis | EPIC | Dev | Dev | Dev | Qa | QA |  | UAT/Train |  |  |  | Deploy
Migration |  |  | includes front end & migration | 1390 | 34.75
CM |  |  | Volume | [39 empty] | UAT | UAT | UAT | Deploy | Deploy
Maternity | [42 empty] | UAT | UAT | UAT | Deploy | Deploy
24 hour nurse line
Serious Illness | [42 empty] | UAT | UAT | UAT | Deploy | Deploy
Home Heart Care
Intensive Weight Management
Patient DecisionSupport
Lifestyle Coaching | [42 empty] | UAT | UAT | UAT | Deploy | Deploy
Assessments/ |  |  | Volume (some of the hours have been used) | 24571 | 614.275 | 61.4275 | 10 |  | Ongoing Requirements/configure/QA
Care Plans | [17 empty] | Care plans will be provided once Heather has the list
Other Integrations/interfaces |  |  |  | TBD | [7 empty] | Requirements can continue | [34 empty] | Deploy
Datamart Reporting (#22) |  |  |  | 700 | 17.5 | 8.75 | 2 | [16 empty] | Requirements | [22 empty] | Deploy
Cadence Group Scheduling (#31) |  |  | Assume 700 hours used for 1:1 | 1800 | 45 | 45 | 1
Kidney integration with CPL/CEE |  |  | Find out more on timelines
Note on A16: Meers, Sherry L: Jeffry Bye owns app
Note on A42: Meers, Sherry L: Unknown if Back-end intergrations

## DATES For PLANNING
10/12-10/16 | 10/19-10/23
EPIC Shared with Digital high level deployment date plan | Share roadmap with larger project team
Raj(Digtial) Integrate EPIC/DIGITAL roadmap- send to Sherry | Leadership for review
Rjaj& Sherry -Review Integration Map with Kim and confrim rationalization on priorities | Integrate with PI Planning

## Remaining Interfaces
These are remaining interfaces not associated with the functionality (MEP, MyChart, Cadence, Auto Status, Lexis, CareEverywhere, healthy planet)

## Assumptions
Things to consider: EPIC Upgrade
QA for next deployment cannot start until Warranty is complete from prior deploymnet

## AHM Roadmap
EPIC ROADMAP |  |  |  | DIGITAL EPIC ROADMAP
2020-12-19 |  |  |  | 2020-12-19
Client & Program Onboarding/Set-Up (F33841/37258)​
12/19: |  |  |  | Send Account, Plan, and Program Extract to Epic Shilpa/Rohith​
Confirmed: |  |  |  | Epic Q&A Pair SetUp & Configuration Swati​
ngTDC |  |  |  | ​
Cadence – individual scheduling |  |  |  | Patient Eligibility/Set-Up Shilpa/Rohith (F33842, F35121​
Global ID |  |  |  | Real Time Eligibility for Patient Set-Up​
5 ngTDC Assessments |  |  |  | Enabler: Eligibility Member Updates (Termination/Merge)​
Operational reporting |  |  |  | Enabler: Member-Plan association​
In parallel: |  |  |  | ​
Kidney Privacy API |  |  |  | Communications Tamesha/Dupesh​
Kidney ADT feed |  |  |  | CKD post engagement letters via SFMC​
SFMC – eliminate manual workaround (kidney letters w/collateral and retain ability for nurse to update letters) |  |  |  | ​
Care Manager Updates (CM Platform Updates to Downstream) Shilpa/Rohith/Swati​
1/1 and beyond: |  |  |  | Source Name as Epic​
January/February |  |  |  | CMDB API​
Care Everywhere – kidney & diabetes |  |  |  | Member Engagement & Interventions (LCC and other AHM-only programs) ​
MyChart w/Video visits - kidney |  |  |  | Enabler: Epic-MEP SSO Sachin/Vinay/AHM​
Auto status updates (Epic enhancement) – need to confirm date (any program) |  | Dependant on upgrade EPIC | no mass enrollment currently | Enabler: MEP-MyChart SSO Sachin/Vinay/AHM​
Other Q1/Date TBD: |  |  |  | Enabler: MEP Integration​
Kidney integration with CPL/CEE |  |  |  | Live Coaching ​
PDM integration | Lexis Nexis |  |  | Enabler: Integrate with Cadence for live coaching use cases Jeff/AHM​
2020-04-01 |  |  |  | 2020-04-01
Remaining programs: CM, Maternity, Serious Illness, Lifestyle Condition Coaching - TBD |  |  |  | Care Manager Updates (CM Platform Updates to Downstream) Shilpa/Swati​
Remaining assessments |  |  |  | Enabler: Send Assessments, Cases, Medication, Labs in Near Real Time​
MEP integration |  |  |  | ​
Cadence Group scheduling (Individual being delivered for 12/19) |  |  |  | Patient Eligibility/Set-Up Shilpa​
Full SFMC functionality |  |  |  | Eligibility Member Updates & Termination​
Remaining interfaces |  |  |  | Member Plan Association​
Healthy Planet |  | HP Link for AAView |  | ​
Member Engagement & Interventions (LCC and other AHM-only programs) AHM​
Post 4/1: |  |  |  | Epic-MEP SSO​
CPL/CEE – ongoing as additional programs transition |  |  |  | MEP-MyChart SSO​
Clinical 360 – when available |  |  |  | MEP Integration​
​
Business Enhancements: |  |  |  | Live Coaching AHM​
Kidney Care PID changes and other program enhancements |  |  |  | Integrate with Cadence for live coaching use cases​
ngTDC care gaps and other program enhancements |  |  |  | ​
New clients |  |  |  | Communications Tamesha/Dupesh​
CKD/ODS Pre-engagement letters via SFMC​
Separate PRF: |  |  |  | Enabler: Communications for other programs​
UM/Tapestry – separate PRF |  |  |  | ​
IPP integration |  |  |  | 2020-07-01
DMS |  |  |  | Care Manager Updates (CM Platform Updates to Downstream)​
Send Assessments, Cases, Medication, Labs in Near Real Time Shilpa/Swati​
​
​
Communications Tamesha/Dupesh​
Communications for other programs​
​
Complete list of features TBD. The scope will depend on the following:​
Milestone/target date of each programs ​
Use cases ​
Solution​
​